## Use cases
# | Feature | Use case | Guest | System Admin | CRDD Head | CRDD Staff | Syllabus Designer | Syllabus Reviewer | Student | Teacher | Use case description
1 | Account List | View all account list Search/Filter account Activate/deactivate account Sort account list Paging |  | X
2 | Account Details | Show all detail of account Edit detail information of account |  | X
3 | Curriculum List | View all curriculum list Search/Filter curriculum Paging Sort | X | X | X | X | X | X | X | X
4 | Curriculum Overview | View curriculum overview | X | X | X | X | X | X | X | X
5 | New Curriculum | Add new curriculum |  | X | X | X
6 | Curriculum Edit | Update curriculum/curriculum detail Delete curriculum/curriculum detail |  | X | X | X
7 | PO List | View all PO list |  | X | X | X | X | X | X | X
8 | PO Details | View PO details |  | X | X | X | X | X | X | X
9 | PO Import | Import PO |  | X | X | X
10 | CLO List | View all CLO list |  | X | X | X | X | X | X | X
11 | CLO Details | View CLO details |  | X | X | X | X | X | X | X
12 | CLO Import | Import CLO |  | X | X | X
13 | CLO-PLO Mapping | View CLO-PLO mapping |  | X | X | X | X | X | X | X
14 | User Login | To log into the system, authenticate, and authorize users. | X | X | X | X | X | X | X | X
15 | User Register | To register a new account within the system. Store user information in the database. | X | X | X | X | X | X | X | X
16 | Password Reset | Allow users to reset their password when forgotten or unable to access their account. |  | X | X | X | X | X | X | X
17 | Content Group List | List all content groups available in the system. |  | X | X | X | X | X | X | X
18 | Content Group Details | Display details about a specific content group. |  | X | X | X | X | X | X | X
19 | Elective List | List all elective courses available in the system. |  | X | X | X | X | X | X | X
20 | Elective Details | Display details about a specific elective course. |  | X | X | X | X | X | X | X
21 | Subject Predecessors | List all prerequisite subjects for a specific subject. | X | X | X | X | X | X | X | X
22 | Subject Sucessors | List all successor subjects for a specific subject. | X | X | X | X | X | X | X | X
23 | Decision Overview | Overview of decisions made in the system. |  | X | X | X | X | X | X | X
24 | Decision List | List all decisions available in the system. |  | X | X | X | X | X | X | X
25 | New Decision | Allow users to create a new decision. |  | X | X | X
26 | Decision Details | Display detailed information about a specific decision. |  | X | X | X | X | X | X | X
33 | Home Page | View the user login section | X | X | X | X | X | X | X | X
34 | New Subject | The process of introducing a new subject or course into an educational |  | X | X | X
35 | New Curriculum Subject | View Curriculum Subject |  | X | X | X
36 | PLO List | View all PLO |  | X | X | X | X | X | X | X
37 | PLO Detail | View PLO details |  | X | X | X | X | X | X | X
38 | PLO Import | Import PLO |  | X | X | X
39 | PLO-PO Mapping | View PLO-PO mapping |  | X | X | X | X | X | X | X
40 | Session List | View all session list, Search session in list |  | X | X | X
41 | Session Details | View session details |  | X | X | X
42 | Session Import | Import session |  | X | X | X
46 | User Profile | Customize users' preferences, settings, and content. |  | X | X | X | X | X | X | X
47 | Password Change | Uupdate passwords as a security measure |  | X | X | X | X | X | X | X
48 | Subject List | View list of all subject |  | X | X | X | X | X | X | X
49 | Subject-PLO mapping | View subject-PLO mapping |  | X | X | X | X | X | X | X
50 | Subject Details | View details of the subject |  | X | X | X | X | X | X | X
51 | Subject Import | Import subject |  | X | X | X
52 | Combo List | View list of combo | X | X | X | X | X | X | X | X
53 | Combo Details | View details of combo |  | X | X | X | X | X | X | X
54 | Syllabus List | View list of all syllabus | X | X | X | X | X | X | X | X
55 | Syllabus Edit | Updates or modifications to an existing syllabus for a course or educational program |  | X | X | X
56 | Syllabus Overview | Providing a concise summary or snapshot of the key components and structure of a course syllabus. | X | X | X | X | X | X | X | X
57 | New Syllabus | Creating a syllabus from scratch for a new course or educational program. |  | X | X | X
58 | Syllabus Import | The process of importing a syllabus from one system |  | X | X | X

## Product
# | Feature | Screen/Function | User Workflow | Syllabus Workflow | Curriculum Workflow | Use Cases | In Charge | Status | SRS | SDS | Planned | Actual | Updated | Update Details
1 | User Access | Home Page | X | X | X | User are presented with an overview of the website's features | Phương Lan | Done | II.1.a | II.1.a | iter1 | iter1 | not yet
2 | User Access | User Register | X |  |  | To register a new account within the system. Store user information in the database. | Phương Lan | Done | II.1.a | II.1.a | iter1 | iter1 | not yet
3 | User Access | User Login | X |  |  | To log into the system, authenticate, and authorize users. | Thượng | Done | II.1.A.b | II.2 | iter1 | iter1 | not yet
4 | User Access | Password Reset |  |  |  | Allow users to reset their password when forgotten or unable to access their account. | Thượng | Done | II.1.A.d | II.4 | iter1 | iter1 | not yet | Update toast, and logut if change pass succes
5 | User Access | User Profile | X |  |  | Allowing users to customize their preferences, settings, and content. | Trình | Done | II.1.a | II.1.a | iter1 | iter1 | not yet | Update toast and show data after input and check data input
6 | User Access | Password Change | X |  |  | Allows users to update their passwords as a security measure | Trình | Done | II.1.a | II.1.a | iter1 | iter1 | not yet
7 | System Admin | Account List | X |  |  | View all account list Search/Filter account Activate/deactivate account Sort account list Paging | Trúc Hà | Done | II.1.B.a | II.7 | iter1 | iter1 | iter4 | Update UI, toast Adding paging, sort Fix modal confirm
8 | System Admin | Account Details | X |  |  | Show all detail of account Edit detail information of account | Trúc Hà | Done | II.1.B.b | II.8 | iter1 | iter1 | iter4 | Update UI, send email password of new account Length check Toast
9 | System Admin | Setting List | X |  |  | View list setting type/ Search name of setting/ allow users to customize their account | Tiến Dũng | Done | II.1.b | II.1.b | iter1 | iter1 | not yet
10 | System Admin | Setting Details | X |  |  | Edit users or assign admin | Tiến Dũng | Done | II.1.b | II.1.b | iter1 | iter1 | iter4 | Type lấy từ combo-box; Value & Display Order & Description ko bắt buộc Descripiton cần đẻ text-area Status để radio đã được fix
11 | Curriculum Management | Curriculum List |  |  | X | View all curriculum list Search/Filter curriculum Paging Sort | Trúc Hà | Done | II.2.A.a | II.11 | iter1 | iter1 | iter4 | Fix UI Remove choosing search criteria Add filter according to assignee & status (some roles after login) Fix date format
12 | Curriculum Management | Curriculum Overview |  |  | X | View curriculum overview | Phương Lan | Done | II.2.a | II.2.a | iter1 | iter1 | not yet
13 | Curriculum Management | New Curriculum |  |  | X | Add new curriculum | Thượng | Done | II.2.A.b | II.12 | iter1 | iter1 | not yet
14 | Curriculum Management | Curriculum Edit |  |  | X | Update curriculum/curriculum detail | Bá Trình | Done | II.2.a | II.2.a | iter1 | iter1 | not yet | update check data input
15 | Subject Management | Subject List |  |  | X | View list of all subject | Tiến Dũng | Done | II.2.b | II.2.b | iter1 | iter1 | not yet
16 | Curriculum Subjects | New Subject |  |  | X | The process of introducing a new subject or course into an educational | Tiến Dũng | Done | II.2.c | II.2.c | iter2 | iter2 | iter4 | đã thêm màn New Subject
17 | Subject Management | Subject-PLO mapping |  |  | X | View subject-PLO mapping | Tiến Dũng | Done | II.2.b | II.2.b | iter2 | iter2 | not yet
18 | Subject Management | Subject Details |  |  | X | View details of the subject | Tiến Dũng | Done | II.2.b | II.2.b | iter2 | iter2 | not yet
19 | Subject Management | Subject Import |  |  | X | Import subject | Thượng | Done | II.2.b | II.2.b | iter2 | iter2 | not yet
20 | Subject Management | Subject Predecessors |  |  | X | List all prerequisite subjects for a specific subject. | Thượng | Done | II.2.b | II.2.b | iter2 | iter2 | not yet
21 | Subject Management | Subject Sucessors |  |  | X | List all successor subjects for a specific subject. | Thượng | Done | II.2.b | II.2.b | iter2 | iter2 | not yet
22 | PLO Management | PLO List |  |  | X | View all PLO | Trình | Done | II.3.b | II.3.b | iter2 | iter2 | not yet | update plo list not show curriculumid
23 | PLO Management | PLO Detail |  |  | X | View PLO details | Trình | Done | II.3.b | II.3.b | iter2 | iter2 | not yet | uncheck curriculum_id and no add curriculum name duplicate
24 | PO Management | PO List |  |  | X | View all PO list | Trình | Done | II.3.a | II.3.1 | iter2 | iter2 | not yet
25 | PO Management | PO Details |  |  | X | View PO details | Trình | Done | II.3.1 | II.3.1 | iter2 | iter2 | not yet
26 | PO Management | PO Import |  |  | X | Import PO | Trình | Done | II.3.1 | II.3.1 | iter2 | iter2 | not yet
27 | Subject Groups | Content Group List |  |  | X | List all content groups available in the system. | Trúc Hà | Done | II.3.C.1 | II.31 | iter2 | iter2 | iter4 | Add more fields (display order, english name), fix UI Add search engine
28 | Subject Groups | Content Group Details |  |  | X | Display details about a specific content group. | Trúc Hà | Done | II.3.C.2 | II.32 | iter2 | iter2 | iter4 | Add more field(display order, english name), fix UI Remove adding subjects Keep subheader
29 | Subject Groups | Elective List |  |  | X | List all elective courses available in the system. | Trúc Hà | Done | II.3.C.3 | II.33 | iter2 | iter2 | iter4 | fix UI Remove delete Toast
30 | Subject Groups | Elective Details |  |  | X | Display details about a specific elective course. | Trúc Hà | Done | II.3.c | II.3.c | iter3 | iter3 | iter4 | fix UI, add elective from subject in curriculum, not create from scratch Toast Keep sub-header
31 | PLO Management | PLO-PO Mapping |  |  | X | View PLO-PO mapping | Trình | Done | II.3.b | II.3.b | iter3 | iter3 | not yet
32 | Decision Management | Decision Overview |  |  | X | Overview of decisions made in the system. | Thượng | Done | II.5.b | II.5.b | iter4 | iter4 | not yet
33 | Decision Management | Decision List |  |  | X | List all decisions available in the system. | Thượng | Done | II.5.b | II.5.b | iter3 | iter3 | not yet
34 | Decision Management | New Decision |  |  | X | Allow users to create a new decision. | Thượng | Done | II.5.b | II.5.b | iter3 | iter3 | not yet
35 | Decision Management | Decision Details |  |  | X | Display detailed information about a specific decision. | Thượng | Done | II.5.b | II.5.b | iter3 | iter3 | not yet
36 | Syllabus List | Syllabus List |  | X |  | View list of all syllabus | Trúc Hà | Done | II.4.a | II.4.a | iter3 | iter3 | iter4 | Add more field, fix UI Toast
37 | Syllabus Edit | Syllabus Edit |  | X |  | Updates or modifications to an existing syllabus for a course or educational program | Trúc Hà | Done | II.4.e | II.4.e | iter4 | iter4 | not yet
38 | Syllabus Overview | Syllabus Overview |  | X |  | Providing a concise summary or snapshot of the key components and structure of a course syllabus. | Trúc Hà | Done | II.4.d | II.4.d | iter3 | iter3 | iter4 | Add more field, fix UI
39 | New Syllabus | New Syllabus |  | X |  | Creating a syllabus from scratch for a new course or educational program. | Trúc Hà | Done | II.4.b | II.4.b | iter4 | iter4 | not yet
40 | Syllabus Import | Syllabus Import |  | X |  | The process of importing a syllabus from one system | Trúc Hà | Done | II.4.c | II.4.c | iter4 | iter4 | not yet
41 | CLO Management | CLO List |  | X |  | View all CLO list | Dũng | To Do | II.4.f | II.4.f | iter3 | iter3 | not yet
42 | CLO Management | CLO Details |  | X |  | View CLO details | Dũng | To Do | II.4.f | II.4.f | iter3 | iter3 | not yet | update CRUD and check name trùng trong syllabus
43 | CLO Management | CLO Import |  | X |  | Import CLO | Dũng | To Do | II.4.f | II.4.f | iter3 | iter3 | not yet
44 | Training Schedule | Session List |  | X |  | View all session list, Search session in list | Trình | To Do | II.4.h | II.4.h | iter3 | iter3 | not yet
45 | Training Schedule | Session Details |  | X |  | View session details | Trình | To Do | II.4.h | II.4.h | iter3 | iter3 | not yet
46 | Training Schedule | Session Import |  | X |  | Import session | Trình | To Do | II.4.h | II.4.h | iter3 | iter3 | not yet | update import if click import show template excel download and import
47 | Curriculum Subjects | New Curriculum Subject |  |  | X | View Curriculum Subject | Dũng | To Do | II.2.c | II.2.c | iter3 | iter3 | not yet
48 | Subject Management | Curriculum Subject Details |  |  | X | Information about each subject or course | Dũng | To Do | II.2.b | II.2.b | iter3 | iter3 | not yet
49 | Subject Groups | Combo List |  |  | X | View list of combo | Thượng | To Do | II.3.c | II.3.c | iter4 | iter4 | not yet
50 | Subject Groups | Combo Details |  |  | X | View details of combo | Thượng | To Do | II.3.c | II.3.c | iter4 | iter4 | not yet

## Iter1
# | Screen / Function | In Charge | Status | Notes
1 | Account List | Trúc Hà | Done
2 | Account Details | Trúc Hà | Done
3 | Curriculum List | Trúc Hà | Done
4 | Subject List | Tiến Dũng | Done
5 | Home Page | Phương Lan | Done
6 | Setting List | Tiến Dũng | Done
7 | Setting Details | Tiến Dũng | Done
8 | User Register | Phương Lan | Done
9 | User Login | Thượng | Done
10 | Password Reset | Thượng | Done
11 | New Curriculum | Thượng | Done
12 | User Profile | Trình | Done
13 | Password Change | Trình | Done
14 | Curriculum Edit | Trình | Done
15 | Curriculum Overview | Phương Lan | Done

## Iter2
# | Screen / Function | In Charge | Status | Notes
1 | PLO List | Bá Trình | Done
2 | PLO Detail | Bá Trình | Done
3 | PO list | Phương Lan | Done
4 | PO details | Phương Lan | Done
5 | PO import | Phương Lan | Done
6 | PLO-PO mapping | Bá Trình | Done
7 | Subject Import | Thượng | Done
8 | New Subject | Tiến Dũng | Done
9 | Subject Detail | Tiến Dũng | Done
7 | Subject Predecessors | Thượng | Done
8 | Subject Successors | Thượng | Done
12 | Subject PLO-mapping | Tiến Dũng | Done
13 | Content Group List | Trúc Hà | Done
14 | Content Group Details | Trúc Hà | Done
15 | Elective List | Trúc Hà | Done

## Iter3
| Screen / Function | In Charge | Status | Notes
1 | Elective Details | Trúc Hà | Done
2 | Syllabus List | Trúc Hà | Done
3 | Syllabus Overview | Trúc Hà | Done
4 | Decision List | Thượng | Done
5 | New Decision | Thượng | Done
6 | Decision Detail | Thượng | Done
7 | Syllabus Edit | Phuong Lan | To Do
8 | New Syllabus | Phuong Lan | To Do
9 | Syllabus Import | Phuong Lan | To Do
10 | Session List | Trình | Done
11 | Session Details | Trình | Done
12 | Session Import | Trình | Done
13 | CLO List | Dũng | Done
14 | CLO Details | Dũng | Done
15 | CLO Import | Dũng | Done
16 | PLO-PO mapping | Trình | Done

## Iter4
# | Screen / Function | In Charge | Status | Notes
1 | Syllabus Edit | Trúc Hà | Done
2 | New Syllabus | Trúc Hà | Done
3 | Syllabus Import | Trúc Hà | Done
4 | New Curriculum Subject | Dũng | Done
5 | Curriculum Subject Details | Dũng | Done
6 | Decision Overview | Thượng | Done
7 | Combo List | Thượng | Done
8 | Combo Details | Thượng | Done
9 | PO list | Trình | Done
10 | PO details | Trình | Done
11 | PO import | Trình | Done