## Issues Report
Title | Description | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Write SRS for Account Details | Write detailed functional specification for the Account Details | Closed | Trúc Hà | 2023-05-18 | 2023-05-28 | iter1 | Done | Account Details
Write SDS for Account Details | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the Account Details | Closed | Trúc Hà | 2023-05-18 | 2023-05-28 | iter1 | Done | Account Details
Write Code for Account Details | Code & Unit test for the Account Details | Closed | Trúc Hà | 2023-05-18 | 2023-05-28 | iter1 | Done | Account Details
Integrate Account Details others | Integrate the Account Details screen with other screens | Closed | Trúc Hà | 2023-05-18 | 2023-05-28 | iter1 | Done | Account Details
Write SRS for Curriculum List | Write detailed functional specification for the Account List | Closed | Trúc Hà | 2023-05-18 | 2023-05-28 | iter1 | Done | Curriculum List
Write SDS for Curriculum List | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the Account List | Closed | Trúc Hà | 2023-05-18 | 2023-05-28 | iter1 | Done | Curriculum List
Write Code for Curriculum List | Code & Unit test for the Account List | Closed | Trúc Hà | 2023-05-18 | 2023-05-28 | iter1 | Done | Curriculum List
Integrate Curriculum List others | Integrate the Account List screen with other screens | Closed | Trúc Hà | 2023-05-18 | 2023-05-28 | iter1 | Done | Curriculum List
Write SRS for Home Page | Write detailed functional specification for the Home Page | Closed | Phuong Lan | 2023-05-18 | 2023-05-28 | iter1 | Done | Home Page
Write SRS for User Register | Write detailed functional specification for User Register | Closed | Phuong Lan | 2023-05-18 | 2023-05-28 | iter1 | Done | User Register
Write SRS for Curriculum Overview | Write detailed functional specification for Curriculum Overview | Closed | Phuong Lan | 2023-05-18 | 2023-05-28 | iter1 | Done | Curriculum Overview
Write SDS for Home Page | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Home Page | Closed | Phuong Lan | 2023-05-18 | 2023-05-28 | iter1 | Done | Home Page
Write SDS for User Register | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the User Register | Closed | Phuong Lan | 2023-05-18 | 2023-05-28 | iter1 | Done | User Register
Write SDS for Curriculum Overview | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Curriculum Overview | Closed | Phuong Lan | 2023-05-18 | 2023-05-28 | iter1 | Done | Curriculum Overview
Write Code for Home Page | Code & Unit test for the Home Page | Closed | Phuong Lan | 2023-05-18 | 2023-05-28 | iter1 | Done | Home Page
Write Code for User Register | Code & Unit test for the User Register | Closed | Phuong Lan | 2023-05-18 | 2023-05-28 | iter1 | Done | User Register
Write Code for Curriculum Overview | Code & Unit test for the Curriculum Overview | Closed | Phuong Lan | 2023-05-18 | 2023-05-28 | iter1 | Done | Curriculum Overview
Write Code for SettingList | Code & Unit test for the SettingList | Closed | Tiến Dũng | 2023-05-18 | 2023-05-28 | iter1 | Done | Setting List
Write Code for SettingDetail | Code & Unit test for the SettingDetail | Closed | Tiến Dũng | 2023-05-18 | 2023-05-28 | iter1 | Done | Setting Detail
Write Code for Subjectist | Code & Unit test for the SubjectList | Closed | Tiến Dũng | 2023-05-18 | 2023-05-28 | iter1 | Done | Subject List
Write SRS for SettingList | Write detailed functional specification for the SettingList | Closed | Tiến Dũng | 2023-05-18 | 2023-05-28 | iter1 | Done | Setting List
Write SRS for SettingDetail | Write detailed functional specification for the SettingDetail | Closed | Tiến Dũng | 2023-05-18 | 2023-05-28 | iter1 | Done | Setting Detail
Write SRS for Subjectist | Write detailed functional specification for the SubjectList | Closed | Tiến Dũng | 2023-05-18 | 2023-05-28 | iter1 | Done | Subject List
Write SDS for SettingList | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the SettingList | Closed | Tiến Dũng | 2023-05-18 | 2023-05-28 | iter1 | Done | Setting List
Write SDS for SettingDetail | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the SettingDetail | Closed | Tiến Dũng | 2023-05-18 | 2023-05-28 | iter1 | Done | Setting Detail
Write SDS for SubjectList | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the SubjectList | Closed | Tiến Dũng | 2023-05-18 | 2023-05-28 | iter1 | Done | Subject List
Write SRS for Account List | Write detailed functional specification for the Account List | Closed | Trúc Hà | 2023-05-18 | 2023-05-28 | iter1 | Done | Account List
Write SDS for Account List | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the Account List | Closed | Trúc Hà | 2023-05-18 | 2023-05-28 | iter1 | Done | Account List
Write Code for Account List | Code & Unit test for the Account List | Closed | Trúc Hà | 2023-05-18 | 2023-05-28 | iter1 | Done | Account List
Integrate Account List others | Integrate the Account List screen with other screens | Closed | Trúc Hà | 2023-05-18 | 2023-05-28 | iter1 | Done | Account List
Write SRS for Login | Write detailed functional specification for Login | Closed | Thượng | 2023-05-18 | 2023-05-28 | iter1 | Done | Login
Write Code for Reset Password | Write detailed functional specification for Reset Password | Closed | Thượng | 2023-05-18 | 2023-05-28 | iter1 | Done | Reset Password
Write SRS for New Curriculum | Write detailed functional specification for New Curriculum | Closed | Thượng | 2023-05-18 | 2023-05-28 | iter1 | Done | New Curriculum
Write SDS for Login | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Login | Closed | Thượng | 2023-05-18 | 2023-05-28 | iter1 | Done | Login
Write Code for Reset Password | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Reset Password | Closed | Thượng | 2023-05-18 | 2023-05-28 | iter1 | Done | Reset Password
Write SDS for New Curriculum | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the New Curriculum | Closed | Thượng | 2023-05-18 | 2023-05-28 | iter1 | Done | New Curriculum
Write Code for Login | Code & Unit test for the Login | Closed | Thượng | 2023-05-18 | 2023-05-28 | iter1 | Done | Login
Write Code for Reset Password | Code & Unit test for the Reset Password | Closed | Thượng | 2023-05-18 | 2023-05-28 | iter1 | Done | Reset Password
Write Code for New Curriculum | Code & Unit test for the New Curriculum | Closed | Thượng | 2023-05-18 | 2023-05-28 | iter1 | Done | New Curriculum
Write SRS for Elective List | Write detailed functional specification for the Elective List | Done | Trúc Hà | 2023-06-01 | 2023-06-11 | iter2 | Done | Elective List
Write SDS for Elective List | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the Elective List | Done | Trúc Hà | 2023-06-01 | 2023-06-11 | iter2 | Done | Elective List
Write Code for Elective List | Code & Unit test for the Elective List | Done | Trúc Hà | 2023-06-01 | 2023-06-11 | iter2 | Done | Elective List
Integrate Elective List others | Integrate the Elective Listscreen with other screens | Done | Trúc Hà | 2023-06-01 | 2023-06-11 | iter2 | Done | Elective List
Write SRS for Content Group List | Write detailed functional specification for the Content Group List | Done | Trúc Hà | 2023-06-01 | 2023-06-11 | iter2 | Done | Content Group List
Write SDS for Content Group List | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the Content Group List | Done | Trúc Hà | 2023-06-01 | 2023-06-11 | iter2 | Done | Content Group List
Write Code for Content Group List | Code & Unit test for the Content Group List | Done | Trúc Hà | 2023-06-01 | 2023-06-11 | iter2 | Done | Content Group List
Integrate Content Group List others | Integrate the Content Group List screen with other screens | Done | Trúc Hà | 2023-06-01 | 2023-06-11 | iter2 | Done | Content Group List
Write SRS for Content Group Details | Write detailed functional specification for the Content Group Details | Done | Trúc Hà | 2023-06-01 | 2023-06-11 | iter2 | Done | Content Group Details
Write SDS for Content Group Details | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the Content Group Details | Done | Trúc Hà | 2023-06-01 | 2023-06-11 | iter2 | Done | Content Group Details
Write Code for Content Group Details | Code & Unit test for the Content Group Details List | Done | Trúc Hà | 2023-06-01 | 2023-06-11 | iter2 | Done | Content Group Details
Integrate Content Group others | Integrate the Content Group Details screen with other screens | Done | Trúc Hà | 2023-06-01 | 2023-06-11 | iter2 | Done | Content Group Details
Write SRS for Subject Import | Write detailed functional specification for the Subject Import | Done | Thượng | 2023-06-01 | 2023-06-11 | iter2 | Done | Elective List
Write SDS for Subject Import | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the Subject Import | Done | Thượng | 2023-06-01 | 2023-06-11 | iter2 | Done | Elective List
Write Code for Subject Import | Code & Unit test for the Subject Import | Done | Thượng | 2023-06-01 | 2023-06-11 | iter2 | Done | Elective List
Write SRS for Subject Predecessor | Write detailed functional specification for the Subject Predecessor | Done | Thượng | 2023-06-01 | 2023-06-11 | iter2 | Done | Content Group List
Write SDS for Subject Predecessor | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the Subject Predecessor | Done | Thượng | 2023-06-01 | 2023-06-11 | iter2 | Done | Content Group List
Write Code for Subject Predecessor | Code & Unit test for the Subject Predecessor | Done | Thượng | 2023-06-01 | 2023-06-11 | iter2 | Done | Content Group List
Integrate Subject Predecessor others | Integrate the Subject Predecessor screen with other screens | Done | Thượng | 2023-06-01 | 2023-06-11 | iter2 | Done | Content Group List
Write SRS for Subject Successor | Write detailed functional specification for the Subject Successor | Done | Thượng | 2023-06-01 | 2023-06-11 | iter2 | Done | Content Group Details
Write SDS for Subject Successor | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the Subject Successor | Done | Thượng | 2023-06-01 | 2023-06-11 | iter2 | Done | Content Group Details
Write Code for Subject Successor | Code & Unit test for the Subject Successor | Done | Thượng | 2023-06-01 | 2023-06-11 | iter2 | Done | Content Group Details
Integrate Subject Successor others | Integrate the Subject Successor screen with other screens | Done | Thượng | 2023-06-01 | 2023-06-11 | iter2 | Done | Content Group Details
Write Code for New Subject | Code & Unit test for the New Subject | Done | Tiến Dũng | 2023-06-01 | 2023-06-11 | iter2 | Done | New Subject
Write Code for Subject Detail | Code & Unit test for the Subject Detail | Done | Tiến Dũng | 2023-06-01 | 2023-06-11 | iter2 | Done | Subject Detail
Write Code for Subject PLO-mapping | Code & Unit test for the Subject PLO-mapping | Done | Tiến Dũng | 2023-06-01 | 2023-06-11 | iter2 | Done | Subject PLO mapping
Write SRS for New Subject | Write detailed functional specification for the New Subject | Done | Tiến Dũng | 2023-06-01 | 2023-06-11 | iter2 | Done | New Subject
Write SRS for Subject Detail | Write detailed functional specification for the Subject Detail | Done | Tiến Dũng | 2023-06-01 | 2023-06-11 | iter2 | Done | Subject Detail
Write SRS for Subject PLO-mapping | Write detailed functional specification for the Subject PLO-mapping | Done | Tiến Dũng | 2023-06-01 | 2023-06-11 | iter2 | Done | Subject PLO mapping
Write SDS for New Subject | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the New Subject | Done | Tiến Dũng | 2023-06-01 | 2023-06-11 | iter1 | Done | New Subject
Write SDS for Subject Detail | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Subject Detail | Done | Tiến Dũng | 2023-06-01 | 2023-06-11 | iter2 | Done | Subject Detail
Write SDS for Subject PLO-mapping | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Subject PLO-mapping | Done | Tiến Dũng | 2023-06-01 | 2023-06-11 | iter2 | Done | Subject PLO mapping
| Code & Unit test for the PO List | Done | Phuong Lan | 2023-06-01 | 2023-06-11 | iter2 | Done | PO List
| Code & Unit test for the PO Details | Done | Phuong Lan | 2023-06-01 | 2023-06-11 | iter2 | Done | PO Details
| Code & Unit test for the PO Import | Done | Phuong Lan | 2023-06-01 | 2023-06-11 | iter2 | Done | PO Import
| Write detailed functional specification for the PO List | Done | Phuong Lan | 2023-06-01 | 2023-06-11 | iter2 | Done | PO List
| Write detailed functional specification for the PO Details | Done | Phuong Lan | 2023-06-01 | 2023-06-11 | iter2 | Done | PO Details
| Write detailed functional specification for the PO Import | Done | Phuong Lan | 2023-06-01 | 2023-06-11 | iter2 | Done | PO Import
| Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the PO List | Done | Phuong Lan | 2023-06-01 | 2023-06-11 | iter2 | Done | PO List
| Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the PO Details | Done | Phuong Lan | 2023-06-01 | 2023-06-11 | iter2 | Done | PO Details
| Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the PO Import | Done | Phuong Lan | 2023-06-01 | 2023-06-11 | iter2 | Done | PO Import
Write SRS for Elective Details | Write detailed functional specification for the Elective Details | Closed | Trúc Hà | 2023-06-14 | 2023-06-26 | iter3 | Done | Elective Details
Write SDS for Elective Details | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the Elective Details | Closed | Trúc Hà | 2023-06-14 | 2023-06-26 | iter3 | Done | Elective Details
Write Code for Elective Details | Code & Unit test for the Elective Details | Closed | Trúc Hà | 2023-06-14 | 2023-06-26 | iter3 | Done | Elective Details
Integrate Elective Details others | Integrate the Elective Details screen with other screens | Closed | Trúc Hà | 2023-06-14 | 2023-06-26 | iter3 | Done | Elective Details
Write SRS for Syllabus List | Write detailed functional specification for the Syllabus List | Closed | Trúc Hà | 2023-06-14 | 2023-06-26 | iter3 | Done | Syllabus List
Write SDS for Syllabus List | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the Syllabus List | Closed | Trúc Hà | 2023-06-14 | 2023-06-26 | iter3 | Done | Syllabus List
Write Code for Syllabus List | Code & Unit test for the Syllabus List | Closed | Trúc Hà | 2023-06-14 | 2023-06-26 | iter3 | Done | Syllabus List
Integrate Syllabus List others | Integrate the Syllabus List screen with other screens | Closed | Trúc Hà | 2023-06-14 | 2023-06-26 | iter3 | Done | Syllabus List
Write SRS for Syllabus Detail | Write detailed functional specification for the Syllabus Detail | Closed | Trúc Hà | 2023-06-14 | 2023-06-26 | iter3 | Done | Syllabus Detail
Write SRS for Syllabus Detail | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the Syllabus Detail | Closed | Trúc Hà | 2023-06-14 | 2023-06-26 | iter3 | Done | Syllabus Detail
Write SRS for Syllabus Detail | Code & Unit test for the Syllabus Detail | Closed | Trúc Hà | 2023-06-14 | 2023-06-26 | iter3 | Done | Syllabus Detail
Write SRS for Syllabus Detail | Integrate the Syllabus Detail screen with other screens | Closed | Trúc Hà | 2023-06-14 | 2023-06-26 | iter3 | Done | Syllabus Detail
Write SRS for Decision List | Write detailed functional specification for the Decision List | Closed | Thượng | 2023-06-14 | 2023-06-26 | iter3 | Done | Decision List
Write SDS for Decision List | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the Decision List | Closed | Thượng | 2023-06-14 | 2023-06-26 | iter3 | Done | Decision List
Write Code for Decision List | Code & Unit test for the Decision List | Closed | Thượng | 2023-06-14 | 2023-06-26 | iter3 | Done | Decision List
Decision List Details others | Integrate the Decision List screen with other screens | Closed | Thượng | 2023-06-14 | 2023-06-26 | iter3 | Done | Decision List
Write SRS for Decision Detail | Write detailed functional specification for the Decision Detail | Closed | Thượng | 2023-06-14 | 2023-06-26 | iter3 | Done | Decision Detail
Write SDS for Decision Detail | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the Decision Detail | Closed | Thượng | 2023-06-14 | 2023-06-26 | iter3 | Done | Decision Detail
Write Code for Decision Detail | Code & Unit test for the Decision Detail | Closed | Thượng | 2023-06-14 | 2023-06-26 | iter3 | Done | Decision Detail
Decision Detail details others | Integrate the Decision Detail screen with other screens | Closed | Thượng | 2023-06-14 | 2023-06-26 | iter3 | Done | Decision Detail
Write SRS for New Decision | Write detailed functional specification for the New Decision | Closed | Thượng | 2023-06-14 | 2023-06-26 | iter3 | Done | New Decision
Write SDS for New Decision | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the New Decision | Closed | Thượng | 2023-06-14 | 2023-06-26 | iter3 | Done | New Decision
Write Code for New Decision | Code & Unit test for the New Decision | Closed | Thượng | 2023-06-14 | 2023-06-26 | iter3 | Done | New Decision
New Decision Details others | Integrate the New Decision screen with other screens | Closed | Thượng | 2023-06-14 | 2023-06-26 | iter3 | Done | New Decision
Write Code for CLO List | Code & Unit test for the CLO List | Done | Dũng | 2023-06-22 | 2023-06-26 | iter3 | Done | CLO List
Write SRS for CLO List | Write detailed functional specification for the CLO List | Done | Dũng | 2023-06-22 | 2023-06-26 | iter3 | Done | CLO List
Write Code for CLO Details | Code & Unit test for the CLO Details | Done | Dũng | 2023-06-22 | 2023-06-26 | iter3 | Done | CLO Details
Write SRS for CLO Details | Write detailed functional specification for the CLO Details | Done | Dũng | 2023-06-22 | 2023-06-26 | iter3 | Done | CLO Details
Write Code for CLO Import | Code & Unit test for the CLO Import | Done | Dũng | 2023-06-22 | 2023-06-26 | iter3 | Done | CLO Import
Write SRS for CLO Import | Write detailed functional specification for the CLO Import | Done | Dũng | 2023-06-22 | 2023-06-26 | iter3 | Done | CLO Import
Write SDS for CLO List | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the CLO List | Done | Dũng | 2023-06-22 | 2023-06-26 | iter3 | Done | CLO List
Write SDS for CLO Details | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the CLO Details | Done | Dũng | 2023-06-22 | 2023-06-26 | iter3 | Done | CLO Details
Write SDS for CLO Import | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the CLO Import | Done | Dũng | 2023-06-22 | 2023-06-26 | iter3 | Done | CLO Import
Write SRS for New Syllabus | Write detailed functional specification for the New Syllabus | Closed | Trúc Hà | 2023-07-01 | 2023-07-15 | iter4 | Done | New Syllabus
Write SDS for New Syllabus | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the New Syllabus | Closed | Trúc Hà | 2023-07-01 | 2023-07-15 | iter4 | Done | New Syllabus
Write Code for New Syllabus | Code & Unit test for the New Syllabus | Closed | Trúc Hà | 2023-07-01 | 2023-07-15 | iter4 | Done | New Syllabus
Integrate New Syllabus others | Integrate the New Syllabus screen with other screens | Closed | Trúc Hà | 2023-07-01 | 2023-07-15 | iter4 | Done | New Syllabus
Write SRS for Syllabus Edit | Write detailed functional specification for the Syllabus Edit | Closed | Trúc Hà | 2023-07-01 | 2023-07-15 | iter4 | Done | Syllabus Edit
Write SDS for Syllabus Edit | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the Syllabus Edit | Closed | Trúc Hà | 2023-07-01 | 2023-07-15 | iter4 | Done | Syllabus Edit
Write Code for Syllabus Edit | Code & Unit test for the Syllabus Edit | Closed | Trúc Hà | 2023-07-01 | 2023-07-15 | iter4 | Done | Syllabus Edit
Integrate Syllabus Edit others | Integrate the Syllabus Edit screen with other screens | Closed | Trúc Hà | 2023-07-01 | 2023-07-15 | iter4 | Done | Syllabus Edit
Write SRS for Syllabus Import | Write detailed functional specification for the Syllabus Import | Closed | Trúc Hà | 2023-07-01 | 2023-07-15 | iter4 | Done | Syllabus Import
Write SRS for Syllabus Import | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the Syllabus Import | Closed | Trúc Hà | 2023-07-01 | 2023-07-15 | iter4 | Done | Syllabus Import
Write SRS for Syllabus Import | Code & Unit test for the Syllabus Import | Closed | Trúc Hà | 2023-07-01 | 2023-07-15 | iter4 | Done | Syllabus Import
Write SRS for Syllabus Import | Integrate the Syllabus Import screen with other screens | Closed | Trúc Hà | 2023-07-01 | 2023-07-15 | iter4 | Done | Syllabus Import
Write Code for New Curriculum Subject | Code & Unit test for the New Curriculum Subject | Done | Tiến Dũng | 2023-07-01 | 2023-07-22 | iter4 | Done | New Curriculum Subject
Write SDS for New Curriculum Subject | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the New Curriculum Subject | Done | Tiến Dũng | 2023-07-01 | 2023-07-22 | iter4 | Done | New Curriculum Subject
Write SRS for New Curriculum Subject | Write detailed functional specification for the New Curriculum Subject | Done | Tiến Dũng | 2023-07-01 | 2023-07-22 | iter4 | Done | New Curriculum Subject
Write Code for Curriculum Subject Details | Code & Unit test for the Curriculum Subject Details | Done | Tiến Dũng | 2023-07-01 | 2023-07-22 | iter4 | Done | Curriculum Subject Details
Write SRS for Curriculum Subject Details | Write detailed functional specification for the Curriculum Subject Details | Done | Tiến Dũng | 2023-07-01 | 2023-07-22 | iter4 | Done | Curriculum Subject Details
Write SDS for Curriculum Subject Details | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the Curriculum Subject Details | Done | Tiến Dũng | 2023-07-01 | 2023-07-22 | iter4 | Done | Curriculum Subject Details
Write SRS for Decision Overview | Write detailed functional specification for the Decision Overview | Closed | Thượng | 2023-07-01 | 2023-07-15 | iter4 | Done | Decision Overview
Write SDS for Decision Overview | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the Decision Overview | Closed | Thượng | 2023-07-01 | 2023-07-15 | iter4 | Done | Decision Overview
Write Code for Decision Overview | Code & Unit test for the Decision Overview | Closed | Thượng | 2023-07-01 | 2023-07-15 | iter4 | Done | Decision Overview
Integrate Decision Overview others | Integrate the Decision Overview screen with other screens | Closed | Thượng | 2023-07-01 | 2023-07-15 | iter4 | Done | Decision Overview
Write SRS for Combo List | Write detailed functional specification for the Combo List | Closed | Thượng | 2023-07-01 | 2023-07-15 | iter4 | Done | Combo List
Write SDS for Combo List | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the Combo List | Closed | Thượng | 2023-07-01 | 2023-07-15 | iter4 | Done | Combo List
Write Code for Combo List | Code & Unit test for the Combo List | Closed | Thượng | 2023-07-01 | 2023-07-15 | iter4 | Done | Combo List
Integrate Combo List others | Integrate the Combo List screen with other screens | Closed | Thượng | 2023-07-01 | 2023-07-15 | iter4 | Done | Combo List
Write SRS for New Combo | Write detailed functional specification for the New Combo | Closed | Thượng | 2023-07-01 | 2023-07-15 | iter4 | Done | New Combo
Write SRS for New Combo | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the New Combo | Closed | Thượng | 2023-07-01 | 2023-07-15 | iter4 | Done | New Combo
Write SRS for New Combo | Code & Unit test for the New Combo | Closed | Thượng | 2023-07-01 | 2023-07-15 | iter4 | Done | New Combo
Write SRS for New Combo | Integrate the Syllabus Import screen with New Combo | Closed | Thượng | 2023-07-01 | 2023-07-15 | iter4 | Done | New Combo
Write SRS for Combo Details | Write detailed functional specification for the Combo Details | Closed | Thượng | 2023-07-01 | 2023-07-15 | iter4 | Done | Combo Details
Write SRS for Combo Details | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the Combo Details | Closed | Thượng | 2023-07-01 | 2023-07-15 | iter4 | Done | Combo Details
Write SRS for Combo Details | Code & Unit test for the Combo Details | Closed | Thượng | 2023-07-01 | 2023-07-15 | iter4 | Done | Combo Details
Write SRS for Combo Details | Integrate the Syllabus Import screen with Combo Details | Closed | Thượng | 2023-07-01 | 2023-07-15 | iter4 | Done | Combo Details